## Test_Execution_Report
TC ID | Scenario ID | Test Case Description | Responsible Tester | Date of Execution | Status | Defect ID - Brief Description | Severity | Status
TC_01 | TS_01 | View course list | Tester 1 | 26/01/2026 | PASS
TC_02 | TS_02 | Apply filter | Tester 2 | 26/01/2026 | PASS
TC_03 | TS_03 | Open course | Tester 2 | 26/01/2026 | PASS
TC_04 | TS_04 | Enroll free course | Tester 3 | 26/01/2026 | PASS
TC_05 | TS_05 | Wishlist course | Tester 3 | 26/01/2026 | PASS
TC_06 | TS_05 | Remove wishlist | Tester 3 | 26/01/2026 | FAIL | BUG_01 - Course not removed from wishlist | Medium | Open
TC_07 | TS_04 | Login required enroll | Tester 3 | 26/01/2026 | PASS
TC_08 | TS_01 | Search course | Tester 1 | 26/01/2026 | PASS
TC_09 | TS_03 | Pagination | Tester 1 | 26/01/2026 | FAIL | BUG_02 - Unable to switch between Multiple course pages | High | Open